## Dashboard
PROJECT RED FLAG - RISK DASHBOARD
Project | Solar Alpha
Location | Solano County, California (fictional demo site)
Overall readiness | 26 | 26
Critical risks | 7
High risks | 8
Risk Factor | Weight | Score (0-100) | Weighted Score
Land | 20% | 38 | 7.6
Law | 20% | 18.6667 | 3.7333
Finance | 25% | 18.6667 | 4.6667
Materials | 20% | 24 | 4.8
Demand | 15% | 34.6667 | 5.2
TOTAL | 100% | 26 | 26

## Risk Register
Risk ID | Factor | Subfactor | Risk | Evidence / Trigger | Likelihood (1-5) | Impact (1-5) | Severity | Owner | Mitigation | Source Document | Risk Score
RF-001 | Land | Site Control | Parcel 14 option unsigned | Collector alignment depends on 18 acres shown as controlled in schedule but unsigned in title file. | 5 | 5 | Critical | Legal / Development | Resolve option or redesign alignment | 01 Land report | 25
RF-002 | Land | Access | Heavy-haul easement language may not permit oversize construction traffic | Primary equipment logistics depend on private agricultural access easement. | 4 | 4 | High | Legal / Logistics | Confirm easement rights and alternate route | 01 Land report | 16
RF-003 | Land | Flood / Drainage | 12% of site mapped flood-prone | Panel layout and civil works may require redesign. | 3 | 3 | Medium | Civil | Update hydrology and layout | 01 Land report | 9
RF-004 | Law | Permitting Sequence | Early grading precedes environmental review milestone | Schedule starts work Oct 14; environmental review/consultation targeted Dec. | 5 | 5 | Critical | Legal / PMO | Validate lawful early works or shift schedule | 03 Legal memo | 25
RF-005 | Law | Habitat Consultation | Protected raptor consultation remains open | Potential seasonal buffer affects 46 acres. | 4 | 5 | Critical | Environmental | Complete consultation and re-layout sensitivity | 02 Environmental assessment | 20
RF-006 | Law | Water | Construction water not fully secured | 82 acre-feet required; only 50 acre-feet indicated. | 4 | 4 | High | Development | Secure balance or alternative source | 02 Environmental assessment | 16
RF-007 | Finance | CAPEX | Model uses stale $186M CAPEX | Updated materials imply $199-211M. | 5 | 5 | Critical | Finance | Rebase cost plan and returns | 07 Finance memo | 25
RF-008 | Finance | Covenant | DSCR falls below 1.25x in updated scenarios | Updated materials = 1.24x; demand corrected = 1.23x. | 5 | 4 | Critical | Finance | Restructure debt / mitigate cost and offtake | 07 Finance memo | 20
RF-009 | Finance | Financing Timing | Debt close precedes largest offtake execution | Financing Oct; Utility A final contract Nov. | 4 | 4 | High | Finance / Commercial | Align conditions precedent and close plan | 05 Demand + 07 Finance | 16
RF-010 | Materials | Transformer | Lead time exceeds schedule by 24 weeks | 62-week supplier indication vs 38-week schedule. | 5 | 5 | Critical | Procurement | Place early order / qualify alternate | 06 Materials report | 25
RF-011 | Materials | Supplier Concentration | Only one qualified transformer supplier | No validated backup for critical-path package. | 4 | 4 | High | Procurement | Qualify second supplier | 06 Materials report | 16
RF-012 | Materials | Price Index | Transformer index +28%, copper +22% | Q1 budget quotes no longer reflect current benchmark. | 4 | 4 | High | Procurement / Finance | Update indexed cost basis | 06 Materials report | 16
RF-013 | Demand | Contract Coverage | Firm contracted demand only 150 MW | Finance model assumes 200 MW firm; LOI for 50 MW is non-binding. | 5 | 5 | Critical | Commercial / Finance | Use 150 MW firm case until contract executed | 05 Demand study | 25
RF-014 | Demand | Customer Concentration | Utility A represents 60% of plant capacity | Largest contract is a single counterparty. | 3 | 4 | High | Commercial | Evaluate concentration limits / credit support | 05 Demand study | 12
RF-015 | Demand | Merchant Exposure | 20% merchant at base, 40% if LOI excluded | Downside forward prices materially reduce coverage. | 4 | 3 | High | Commercial | Hedge or add contracted buyer | 05 Demand study | 12
RF-016 | Land | Community | Fallback truck route conflicts with stakeholder request | Eastern residential road opposed by adjacent landowners. | 4 | 3 | High | Community / Logistics | Agree routing protocol before hearing | 04 Community report | 12

## Scoring
Factor | Weight | Avg Risk Score | Max Risk Score | Critical Count | High Count | Readiness Score
Land | 20% | 15.5 | 25 | 1 | 2 | 38
Law | 20% | 20.3333 | 25 | 2 | 1 | 18.6667
Finance | 25% | 20.3333 | 25 | 2 | 1 | 18.6667
Materials | 20% | 19 | 25 | 1 | 2 | 24
Demand | 15% | 16.3333 | 25 | 1 | 2 | 34.6667

## Evidence Map
Source Document | Primary Factor | Key Fields | Seeded Red Flag
01_Land_and_Site_Due_Diligence.pdf | Land | site control; easements; slope; flood; geotech | Unsigned Parcel 14 + heavy-haul easement ambiguity
02_Environmental_Water_and_Biodiversity_Assessment.pdf | Law / Land | habitat; wetlands; water; drainage | Raptor buffer conflict + 32 acre-feet water gap
03_Legal_Regulatory_and_Permitting_Memo.pdf | Law | approval sequence; historical timing; dependencies | Early works precede environmental milestone
04_Community_and_Stakeholder_Engagement_Report.pdf | Land / Law | stakeholders; sentiment; commitments | Fallback truck route conflicts with community request
05_Demand_and_Offtake_Market_Study.pdf | Demand | contracted MW; merchant share; price index | Only 150 MW firm vs 200 MW assumed
06_Materials_Supply_Chain_and_Price_Index.pdf | Materials | indices; lead times; supplier concentration | Transformer 62 weeks vs 38 weeks schedule
07_Financial_Feasibility_and_Sensitivity_Memo.pdf | Finance | CAPEX; IRR; DSCR; financing conditions | $186M model conflicts with $199-211M updated cost