## Material Indices
Material | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Material | Aug Index | Schedule Lead Time | Supplier Count
Power transformers | 100 | 103 | 108 | 112 | 118 | 121 | 125 | 128 | Power transformers | 128 | 62 | 1
Steel structures | 100 | 101 | 104 | 108 | 111 | 114 | 116 | 117 | Steel structures | 117 | 28 | 3
Copper cable | 100 | 102 | 106 | 109 | 113 | 117 | 120 | 122 | Copper cable | 122 | 24 | 2
Battery containers | 100 | 100 | 101 | 103 | 105 | 106 | 108 | 109 | Battery containers | 109 | 34 | 2
PV modules | 100 | 99 | 98 | 97 | 96 | 95 | 95 | 94 | PV modules | 94 | 18 | 4
Synthetic benchmark - Jan 2026 = 100

## Demand Index
Metric | 2028 | 2029 | 2030 | 2031 | 2032
Base forward price | 47.5 | 49 | 50.4 | 51.7 | 52.9
Downside forward price | 35 | 36.5 | 37.2 | 38 | 39.1
Upside forward price | 58 | 60 | 61.5 | 63 | 64.5
Firm contracted MW | 150 | 150 | 150 | 150 | 150
Non-binding LOI MW | 50 | 50 | 50 | 50 | 50
Merchant MW | 50 | 50 | 50 | 50 | 50
Total plant MW | 250 | 250 | 250 | 250 | 250
Customer / Segment | MW | Binding? | Concentration | Key condition
Utility A | 150 | Term sheet | 60% | Final contract after interconnection milestone
Data Center Consortium | 50 | No | 20% | Termination right pre-interconnection
Merchant | 50 | N/A | 20% | Spot / forward exposure
TOTAL | 250 |  | 100%

## Critical Dependencies
Dependency | Required By | Current Evidence Date | Gap (weeks) | Risk Factor | Status
Parcel 14 site control | 2026-09-15 | 2026-08-14 | -4.5714 | Land | Open
Environmental review | 2026-10-14 | 2026-12-08 | 7.8571 | Law | Conflict
Construction water agreement | 2026-10-01 | 2026-11-15 | 6.4286 | Law | Conflict
Transformer delivery | 2027-12-01 | 2028-05-17 | 24 | Materials | Conflict
Utility A final offtake | 2026-10-15 | 2026-11-30 | 6.5714 | Demand | Conflict
Financing close | 2026-10-15 | 2026-10-15 | 0 | Finance | Target